## Project Tracker
Project Tracker
| Percent Over/Under to Flag | 25%
Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2023-02-09 | 2023-04-10 | 210 | 61 | 2023-02-09 | 2023-04-15 | 1 | 300 | 0 | 66
Project 2 | Category 2 | Employee 4 | 2023-03-05 | 2023-04-05 | 400 | 30 | 2023-03-05 | 2023-04-08 | 0 | 390 | 0 | 33
Project 3 | Category 1 | Employee 2 | 2023-01-05 | 2023-03-06 | 500 | 61 | 2023-01-05 | 2023-03-19 | 0 | 500 | 0 | 74
Project 4 | Category 2 | Employee 3 | 2023-01-15 | 2023-01-25 | 250 | 10 | 2023-01-15 | 2023-02-03 | 0 | 276 | 1 | 18
Project 5 | Category 3 | Employee 2 | 2023-01-15 | 2023-02-24 | 300 | 39 | 2023-01-15 | 2023-03-02 | 0 | 310 | 0 | 47
Project 6 | Category 4 | Employee 4 | 2023-02-14 | 2023-02-24 | 500 | 10 | 2023-02-14 | 2023-03-01 | 0 | 510 | 1 | 17
Project 7 | Category 5 | Employee 1 | 2023-03-02 | 2023-03-26 | 750 | 24 | 2023-03-02 | 2023-03-31 | 0 | 790 | 0 | 29
Project 8 | Category 2 | Employee 1 | 2023-03-07 | 2023-04-15 | 450 | 38 | 2023-03-01 | 2023-04-10 | 0 | 430 | 0 | 39
Project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS